## Sheet1
Chapter 430 Flight Plan 2019-2023
rev 1.0 12-2018
Chapter 430's Mission -
Support the mission, vision, goals and objectives of EAA. Create an environment to nuture growth of recreational aviation in our community, focus on flight safety, education, aircraft building, maintenance, innovation and the Young / Senior Eagle Program
1 | Chapter Marketing
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
1.1 | Increase Chapter awareness at our airport | Utilize customized chapter promo materials (rack cards, fliers, business cards) around the airport. Write personal letters to each of the hangar renters/owners on the airfield about the EAA Chapter and its benefits | Increase membership | Complete by March 2018 | Program and Membership teams
1.2 | Increase Chapter visibility in our region | Advertise chapter events (fly-ins, open house, gatherings, etc.) via ChapterBlast, Social Flight, and EAA Calendar of Events Facebook | Create Chapter awareness off airport - grow membership | Complete by May 2018 | Program and Membership teams
1.3 | Create visibility within city admin | Attend City Airport Advisory meetings & city council meetings | Create visibility and value at city management level | 2nd Tuesday each month, 6pm City Council meeting | Program and Membership teams
2 | Chapter Activities
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
2.1 | Host Chapter Burger Burn/Open House Fly-In | Organize first chapter fly-in and burger burn. Charge $5 per plate. Serve burgers, hot dogs, chips, and soda. | Raise Money, grow awareness, gain 1-2 members | June/July 2018 | Program Chair
2.2 | Host Young Eagle Rallies | Using resources provided by the EAA Chapter and Young Eagle office, organize two Young Eagles rallies each year. (May and Sept.) | Introduce kids ages 8-17 to the basics of airplanes, airports and careers | February 15th May, June, July, | Young Eagle Chairperson present plan to board
2.3 | Fly Out | Informal gathering of pilots to fly to local area airports or other events | Have fun and build a bond of fliers | Events planned | Flyout Chairperson Barry Halstead
3 | Airplane Building & Maintenance
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
3.1 | Encourage building at the chapter level | Host a Sport Air Workshop in Spring 2018 | Demonstrate basic building concepts to area members | November 1st | Tech Advisors
3.2 | Chapter Maintenance Clinic | Demonstrate and show various task owners can perform on their own aircraft | Increase knowledge and owner confidence | Feb, April, June, July | Tech Advisors
3.3 | Encourage building at the chapter level | Solicit work bench, tool and equipment & donations for Chapter 430's "Builders Corner" | Provide tools and equipment to chapter members who don't have access to them | September 30th | Tech Advisors
4 | Flight Safety
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
4.1 | Establish a VMC Club | Set up an VMC Club. Host one meeting each month Second Wednesday 1900 Mariners Café Sequim | Encourage safe flying and good decision making | Started September 2017 | Ray Ballantyne & Team
4.2 | Host an FAA Faast Seminar | Host FAA FAASTeam twice a year | Encourage members to take part in the FAA Wings Program | Contact FAA February 2018 | Deb Cox / Dave Miller / Ray Ballantyne
5 | Chapter Fundraising
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
5.1 | Develop Plan for chapter home | Identify the scope of work and detail a plan for implementation | Phase I | March 2018 | TBD
5.2 | Raise money for chapter home | Host 4 Pancake Breakfast/year. (April, June, August, Oct.) | Avg x attendees @ $3 net profit of $x/event or $/year | Fundraising planning starts ASAP. | (Fundraising Chair) TBD
5.3 | Raise money to purchase chapter home | Try to Host EAA Tri-Motor during the summer of 20?? | Raise $2000.00 | Contact EAA Air-Tours department by ASAP | (Fundraising Chair) TBD
5.4 | Develop Benevolence | Develop marketing / informaiton sheets for members who are interested |  | Start as soon as as chair est. | (Fundraising Chair) TBD